## Risk Register
Project ATI (Automated Ticketing Initiative) — Risk Register
Chiltern Vale Borough Council — Customer & Digital Services ¦ Last reviewed: 1 April 2026 ¦ Owner: Daniel Osei, Project Manager
Risk ID | Risk Description | Category | Likelihood | Impact | Severity Rating | Owner | Mitigation / Action | Status | Date Raised | Last Reviewed
R01 | Data migration from CustomerFirst results in incomplete or corrupted records (8% mismatch identified in dry-run test) | Data | High | High | Red | Aisha Bello | Root cause analysis under way following the 30 March dry-run test; remediation plan due at the 15 April 2026 Board meeting | Open | 20/02/2026 | 01/04/2026
R02 | Northbridge (supplier) resourcing changes cause delays to build/UAT | Supplier | Medium | High | Amber | Daniel Osei | Dedicated engineer reassigned to the Council from 2 April 2026; monitor via weekly supplier call | Open | 20/02/2026 | 01/04/2026
R03 | Avaya telephony integration requires unbudgeted change request (est. £18,000) | Financial | Medium | Medium | Amber | Robert Fairweather | Business case being prepared for Programme Board approval on 8 April 2026 | Open | 20/03/2026 | 01/04/2026
R04 | Compressed UAT cycle (6 weeks reduced to 4) increases risk of undetected defects | Quality | Medium | High | Amber | Priya Chandaria | Weekly UAT coverage review introduced; extended daily test sessions | Open | 01/04/2026 | 01/04/2026
R05 | Training resource (Chloe Sutton) shared with concurrent waste contract renewal campaign | Resourcing | Medium | Medium | Amber | Margaret Ellison | Backfill support to be discussed with Head of Communications | Open | 01/04/2026 | 01/04/2026
R06 | Go-live date (17 Jun 2026) clashes with Council Tax annual billing enquiry peak | Operational | Low | Medium | Green | Margaret Ellison | To be reviewed alongside the go-live date decision at the 15 April 2026 Board meeting | Open | 04/03/2026 | 01/04/2026
R07 | Budget contingency reduced by unplanned change requests | Financial | Low | Medium | Green | Tom Radcliffe | Monitor spend against £480,000 approved budget monthly | Open | 03/04/2026 | 01/04/2026