Chiltern Vale Borough Council

Project ATI – Status Update

Monthly Project Status Update

Prepared by: Daniel Osei, Project Manager

Date issued: 04/03/2026

Reporting period: 20/02/2026 – 04/03/2026

Overall severity status: GREEN

# 1. Summary

Project ATI remains on track. System configuration is progressing well and the data migration approach has been agreed with Northbridge Digital Solutions. No major issues to report this period.

# 2. Progress this period

- System configuration approximately 70% complete.

- Data migration design on track for sign-off by 27 March.

- UAT planning under way; UAT expected to start 6 April.

- Telephony integration (Avaya) requirements confirmed with Northbridge; no issues anticipated – integration expected to be straightforward using ServicePoint’s standard Avaya connector.

- Training needs analysis started.

# 3. Current position against milestones

All milestones are currently on track. Go-live remains targeted for 28 May 2026.

Budget: £198,000 spent of £480,000 approved (41%).

# 4. Key issues / delays

None significant at this time. Minor resourcing pressure is anticipated around May due to overlap with waste contract renewal work, but this is considered manageable.

# 5. Priorities for next period

- Finalise data migration design and secure sign-off.

- Complete UAT test script development.

- Begin telephony integration build.